## Migration Plan
| Task | SOP/Links | Owning Team | Owner | Status | Due Date | Notes | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 | 2026-05-01 | 2026-05-02 | 2026-05-03
1 | Discovery & Design
1.1 | Verify App Execution team has the proper access to source AWS account and AERO AWS |  | App Ex | Abhishek T | Complete
1.2 | Verify App Factory team has the proper access to source AWS account and AERO AWS |  | App Factory | Josh S | Complete
1.3 | Create a AERO & HON ASN | ASN Create | App Ex | Abhishek T | In Progress | 2026-03-13 | 3/16: ASNs requested, approved by SO, pending questions to be answered 3/13: Requests submitted Decision on ASN made 3/12, ASN creation to follow for both HON and AERO
1.4 | Update ASN Disposition |  | App Factory | Josh S | In Progress | 2026-03-13 | Defined with ASN requests
1.5 | Gather Account Deployment Prerequisites |  | App Ex | Abhishek T | Complete
1.6 | AWS Account Setup (Landing Zone Creation) AERO & HON |  | App Factory | Josh S | In Progress | 2026-03-13 | 3/17: LZ for AERO complete, HON pending 3/16: CC aligned, LZ requests sent 3/13: Created for AERO QA/PROD. HON was submitted, Use Same CC as AERO; 3/13: DB VPC Created for AERO
1.7 | Server is ready AERO & HON |  |  | Muthu | In Progress | 2026-03-16 | 3/18: Server added to domain, ETA 3/18 3/16: HON in progress with security open items, ETA 3/16 3/13: Server is ready for AERO
1.8 | Complete the AWS resource tracker & Open a teams chat (with app name) for this build |  | App Ex | Abhishek T | In Progress | 2026-03-16
1.9 | Submit the Change Request |  | App Ex | Jason K | In Progress | 2026-03-17 | 3/17: QA CR submitted (CHG0493642)
1.1 | Build Plan sign-off |  | App Ex | Abhishek T | In Progress | 2026-03-20
2 | AWS Readiness Essentials
2.1 | Create any AERO AD groups and required certificates | IAM Services | App Ex | Abhishek T | In Progress | 2026-03-17 | 3/18: Request to Jan on existing AD Groups. AD group may not exist. Abhishek - confirm AD group and SSL requirements 3/16: Reviewed SOP, to get started 3/16
2.2 | Upload certificates to AWS certificate manager on target account (landing zone) | Cert Request | App Factory | Josh S | Blocked | 2026-03-18 | AD group (HON and Aero) required before requesting certificates
QA - Aero and HON
3 | Infrastructure Readiness
3.1 | IAM Permission Mirroring/ Copy AMIs from source environement |  | App Factory | Srikanth K | Complete | 2026-03-16 | 3/16: Non-PROD complete;
3.2 | Gather approval from VM team to use new AMI |  | App Factory | Josh S | Complete | 2026-03-17 | 3/16: Approved through 2027
3.3 | Database migration planning |  | App Factory (DB Team) | Tanaji T / Rutuja | Not Started | 2026-03-17
3.4 | Deploy any VPC endpoints |  | App Factory | Josh S | N/A | 2026-03-18 | N/A
3.5 | Deploy serverless AWS services (RDS Database) |  | App Factory / App Ex | Josh S / Abhishek T | Not Started | 2026-03-18 | 3/16: Jason to connect with Tanaji on progress, open questions Require meeting with DB and App teams to confirm requirements. Tools available by AWS to perform. Working session required/complete.
3.6 | Deploy compute instances (EC2) |  | App Factory / App Ex | Josh S / Abhishek T | In Progress | 2026-03-19 | 3/16: HON TBD 3/13: Done for Aero
3.7 | Deploy Security groups (EC2) |  | App Factory | Josh S | In Progress | 2026-03-19 | 3/16: HON TBD 3/13: Done for Aero
3.8 | Confirm source, destination and port for traffic leaving the AWS Account |  | App Factory / App Ex | Josh S / Abhishek T | Not Started | 2026-03-20
3.9 | Submit Firewall Requests to make sure VPCs can communicate and downstream applications can receive outbound traffic |  | App Factory / App Ex | Josh S / Abhishek T | Not Started | 2026-03-20
3.1 | Test connecitvity post firewall request |  | App Factory | Josh S | Not Started | 2026-03-20
3.11 | Database migration |  | App Factory | Tanaji T / Rutuja | Not Started | 2026-03-23 | VPC and CR required
3.12 | Verify connectivity to the newly migrated database |  | App Factory | Josh S | Not Started | 2026-03-23
3.13 | Service Readiness Verification |  | App Factory | Josh S | Not Started | 2026-03-23
3.14 | Handoff of completed resource tracker to Application Execution team |  | App Factory | Josh S | Not Started | 2026-03-24
4 | Application Readiness
4.1 | Application Configuration |  | HON / App Ex |  | Not Started | 2026-03-24 | 3/16: JoVi to host call discussing for HON 3/18, to report back Will start as is from Aero
4.2 | Service Configuration |  | HON / App Ex |  | Not Started | 2026-03-24
4.3 | Application Smoke Testing |  | HONAERO |  | Not Started | 2026-03-25
4.4 | Complete Post-Migration Checklist |  | App Ex |  | Not Started | 2026-03-25
4.5 | Submit any final DNS requests |  | App Ex |  | Not Started | 2026-03-25
4.6 | Technical Support |  | App Factory |  | Not Started | 2026-03-25
4.7 | Rollback decision |  | App Ex |  | Not Started | 2026-03-26
4.8 | Rollback if required |  | App Ex |  | Not Started | 2026-03-26
4.9 | Complete Post-Migration Checklist (Post-Build) |  | App Ex |  | Not Started | 2026-03-27
5 | Application Testing
5.1 | System Integration Testing (SIT) |  | App Ex |  | Not Started | 2026-03-25
5.2 | Review & Approval (TG2) |  | HONAERO |  | Not Started | 2026-03-27
5.3 | Regression Testing/ UAT |  | HONAERO |  | Not Started | 2026-03-31
5.4 | Technical Support |  | App Factory |  | Not Started
PROD
6 | Infrastructure Readiness
6.1 | IAM Permission Mirroring/ Copy AMIs from source environement |  | App Factory | Srikanth K | In Progress | 2026-04-05
6.2 | Gather approval from VM team to use new AMI |  | App Factory | Josh S | Not Started | 2026-04-06
6.3 | Database migration planning |  | App Factory (DB Team) | Vasudevan KV | Not Started | 2026-04-06
6.4 | Deploy any VPC endpoints |  | App Factory | Josh S | Not Started | 2026-04-10
6.5 | Deploy serverless AWS services (RDS Database) |  | App Factory / App Ex | Josh S / Abhishek T | Not Started | 2026-04-10
6.6 | Deploy compute instances |  | App Factory / App Ex | Josh S / Abhishek T | Not Started | 2026-04-10
6.7 | Deploy Security groups |  | App Factory | Josh S | Not Started | 2026-04-10
6.8 | Submit Firewall Requests to make sure VPCs can communicate and downstream applications can receive outbound traffic |  | App Factory / App Ex | Josh S / Abhishek T | Not Started | 2026-04-15
6.9 | Test connecitvity post firewall request |  | App Factory | Josh S | Not Started | 2026-04-16
6.1 | Database migration |  | App Factory | Josh S | Not Started | 2026-04-19
6.11 | Verify connectivity to the newly migrated database |  | App Factory | Josh S | Not Started | 2026-04-19
6.12 | Service Readiness Verification |  | App Factory | Josh S | Not Started | 2026-04-19
6.13 | Handoff of completed resource tracker to Application Execution team |  | App Factory | Josh S | Not Started | 2026-04-20
7 | Application Readiness
7.1 | Application Configuration |  | HON / App Ex |  | Not Started | 2026-04-22
7.2 | Service Configuration |  | HON / App Ex |  | Not Started | 2026-04-22
7.3 | Application Smoke Testing |  | HONAERO |  | Not Started | 2026-04-27
7.4 | Complete Post-Migration Checklist |  | App Ex |  | Not Started | 2026-04-27
7.5 | Submit any final DNS requests |  | App Ex |  | Not Started | 2026-04-27
7.6 | Technical Support |  | App Factory |  | Not Started | 2026-04-27
7.7 | Rollback decision |  | App Ex |  | Not Started | 2026-04-27
7.8 | Rollback if required |  | App Ex |  | Not Started | 2026-04-28
7.9 | Complete Post-Migration Checklist (Post-Build) |  | App Ex |  | Not Started | 2026-04-29
8 | Application Testing
8.1 | System Integration Testing (SIT) |  | App Ex |  | N/A
8.2 | Review & Approval (TG2) |  | HONAERO |  | N/A
8.3 | Regression Testing/ UAT |  | HONAERO |  | N/A
8.4 | Technical Support |  | App Factory |  | N/A

## Key Contacts
HONEYWELL
Jan Horky
Martin Vagovszky
Alex Schneider |  | HON cloud architect
Andrew Wade |  | HON cloud architect
Michael Gilliland | michael.gilliland@honeywell.com
Tom Kleinau | tom.kleinau2@honeywell.com
JoVi venkataraman | jothyvijay.venkataraman@honeywell.com | SO
Sahil Arya
Vijaykumar Vaikunthe
PwC
Srikanth Kashapaka | srikanth.kashapaka@pwc.com
Muthumariappan S M | muthu.mariappan.s.m@pwc.com | App Factory (Cloud)
Josh Sarkis | joshua.sarkis@pwc.com | App Factory (Cloud)
Tristan Oetker | tristan.oetker@pwc.com | App Factory (Cloud)
Gautum Gulati | gautam.gulati@pwc.com | DB
Tanaji T
Kharanshu S

## Notes
| AERO | [5 empty] | New Honeywell
| QA |  | Prod |  |  |  | QA |  | PROD
| Field | Value | Field | Value | Remarks | Action Item | Field | Value | Field | Value | Remarks | Action Item
| SBG | Aero | SBG | Aero |  |  | SBG | Aero | SBG | Aero
| SBU / SBE | Control Systems, Divest, E&PS, EDS, ES, Other PL, S&C | SBU / SBE | Control Systems, Divest, E&PS, EDS, ES, Other PL, S&C |  | Get from Reetam Pal | SBU / SBE | Use consistent values | SBU / SBE | Use consistent values
| Product | ONESOURCE FOR ENGINEERING 8.0 QA | Product | ONESOURCE FOR ENGINEERING 8.0 PROD |  |  | Product | ONESOURCE FOR ENGINEERING 8.0 QA | Product | ONESOURCE FOR ENGINEERING 8.0 PROD
| Application Service Number | ASN0000261 | Application Service Number | ASN0000981 |  |  | Application Service Number | [Enter number] AERO ASN (PMO/app owner team need to create) | Application Service Number | [Enter number] AERO ASN (PMO/app owner team need to create)
| Cost Center |  | Cost Center |  | Cloud Team has details |  | Cost Center |  | Cost Center
| Environment | NonProd | Environment | Prod |  |  | Environment | NonProd | Environment | Prod
| Estimated Annual Spend | Put aprox cost if known, if not known put 1000 | Estimated Annual Spend | Put aprox cost if known, if not known put 1000 |  | Need to revise with DB estimates | Estimated Annual Spend | Put aprox cost if known, if not known put 1000 | Estimated Annual Spend | Put aprox cost if known, if not known put 1000
| Approved in Annual Operating Plan | Yes | Approved in Annual Operating Plan | Yes |  |  | Approved in Annual Operating Plan | Yes | Approved in Annual Operating Plan | Yes
| Subscription Contact | Jothy Vijay | Subscription Contact | Jothy Vijay |  |  | Subscription Contact | Resource contact | Subscription Contact | Resource contact
| Alternate Contact | Sreekanth Guntaka | Alternate Contact | Sreekanth Guntaka |  |  | Alternate Contact | Secondary resource contact (or same as primary if there are not multiple) | Alternate Contact | Secondary resource contact (or same as primary if there are not multiple)
| Region |  | Region | Specify required networking region |  | Muthu will update the region | Region | Specify required networking region | Region | Specify required networking region
| App Subnet Space | [Enter subnet space] | App Subnet Space | [Enter subnet space] | Cloud Team has details |  | App Subnet Space | [Enter subnet space] | App Subnet Space | [Enter subnet space]
| Database Subnet Space | [Enter subnet space] | Database Subnet Space | [Enter subnet space] | Cloud Team has details |  | Database Subnet Space | [Enter subnet space] | Database Subnet Space | [Enter subnet space]
| Cloud Group for Subscription Assignment | CL.AWSCOM.AERO-PWCMigration-Contributor | Cloud Group for Subscription Assignment | CL.AWSCOM.AERO-PWCMigration-Contributor |  |  | Cloud Group for Subscription Assignment | CL.AWSCOM.AERO-PWCMigration-Contributor | Cloud Group for Subscription Assignment | CL.AWSCOM.AERO-PWCMigration-Contributor
[7 empty] | Version | 8
[7 empty] | SBG | IA
[7 empty] | BU | IA HQ
[7 empty] | Run/Operation Contact | Arya, Sahil
[7 empty] | Run/Operations Escalation | Vaikunthe, Vijaykumar
[7 empty] | Support Group | MBE Tool support
[7 empty] | Road Map | Retain
[7 empty] | Credit Card Payments | No
[7 empty] | Already dev/in use? | Yes
|  |  | Additional Attributes | AERO |  |  | Additional Attributes | HONEYWELL
Josh 3/13: | The Prod Aero account is created
The non-prod EC2 is deployed from the AMS AMI and the new admin credentials have been set.
The Honeywell DCN team is currently installing their security tool stack on the new EC2
We are working on submitting a new servicenow request for Honeywell Prod and Non-prod and will continue to escalate through the email thread.

## Archive
| Task | Owning Team | Owner | Status
1 | Discovery & Design |  |  | In Progress
1 | Verify App Execution team has the proper access to source AWS account and HON AWS | App Ex | Abhishek T | In Progress
1.1 | Verify App Factory team has the proper access to source AWS account and HON AWS | App Factory | Josh S | In Progress
1.2 | Create an AERO/New Honeywell ASN | N/A | N/A | N/A
1.3 | Update ASN Disposition | App Factory | Josh S | In Progress
1.4 | Gather Account Deployment Prerequisites | App Ex | Abhishek T | In Progress | Josh escalated 3/9
1.5 | AWS Account Setup (Landing Zone Creation) | App Factory | Josh S | Complete
1.6 | Complete the AWS resource tracker & Open a teams chat (with app name) for this build | App Ex | Abhishek T
1.7 | Submit the Change Request | App Ex | Jason K
2 | AWS Readiness Essentials
2.1 | Create any HON AD groups and required certificates | App Ex | Abhishek T
2.2 | Upload certificates to AWS certificate manager on target account (landing zone) | App Factory | Josh S
3 | Infrastructure Readiness
3 | IAM Permission Mirroring/ Copy AMIs from source environement | App Factory
3.1 | CI/CD Setup | App Ex
3.2 | Database migration planning | App Factory (DB Team)
3.3 | Deploy any VPC endpoints | App Factory
3.4 | Deploy serverless AWS services | App Factory / App Ex
3.5 | Deploy compute instances | App Factory / App Ex
3.6 | Deploy Security groups | App Factory
3.7 | Deploy Load Balancers | App Factory
3.8 | Create DNS entries for new load balancers | App Ex
3.9 | Confirm source, destination and port for traffic leaving the AWS Account | App Factory / App Ex
3.1 | Submit Firewall Requests to make sure VPCs can communicate and downstream applications can receive outbound traffic | App Factory / App Ex
3.11 | Test connecitvity post firewall request | App Factory
3.12 | Database migration | App Factory
3.13 | Verify connectivity to the newly migrated database | App Factory
3.14 | Service Readiness Verification | App Factory
3.15 | Handoff of completed resource tracker to Application Execution team | App Factory
4 | Application Readiness
4 | Application Configuration | App Ex
| Need config steps for HON instances | HON
4.1 | Service Configuration | App Ex
4.2 | Data Assessment | HON
4.3 | Data Clean Up (if applicable) | HON
4.4 | Data Validation (post clean up only) | HON
4.5 | Configure CI/CD Pipelines (if applicable) | HON
4.6 | Application Smoke Testing | HON
4.7 | Complete Post-Migration Checklist | App Ex
4.8 | Submit any final DNS requests | App Ex
4.9 | Technical Support | App Factory
5 | Rollback decision | App Ex
5.1 | Rollback if required | App Ex
5.2 | Complete Post-Migration Checklist (Post-Build) | App Ex
5 | Application Testing
5 | System Integration Testing (SIT) | App Ex
5.1 | Review & Approval (TG2) | HON
5.2 | Regression Testing/ UAT | HON
5.3 | Technical Support | App Factory

## 1SFE_PROD1
| Task | SOP/Links | Owning Team | Owner | Status | Due Date | Notes
1 | Discovery & Design |  |  |  | In Progress
1 | Verify App Execution team has the proper access to source AWS account and AERO AWS |  | App Ex | Abhishek T | Complete
1.1 | Verify App Factory team has the proper access to source AWS account and AERO AWS |  | App Factory | Josh S | Complete
1.2 | Create an AERO / HON ASN | ASN Create | App Ex | Abhishek T | In Progress | 2026-03-13 | Decision on ASN made 3/12, ASN creation to follow for both HON and AERO
1.3 | Update ASN Disposition |  | App Factory | Josh S | In Progress | 2026-03-13
1.4 | Gather Account Deployment Prerequisites |  | App Ex | Abhishek T | Complete
1.5 | AWS Account Setup (Landing Zone Creation) |  | App Factory | Josh S | Blocked | 2026-03-13 | 3/12: Rejected due to cost center, open questions remain
1.6 | Complete the AWS resource tracker & Open a teams chat (with app name) for this build |  | App Ex | Abhishek T | In Progress | 2026-03-16 | Link
1.7 | Submit the Change Request |  | App Ex | Jason K | Not Started | 2026-03-17
2 | AWS Readiness Essentials |  |  |  | Not Started
2.1 | Create any AERO AD groups and required certificates | IAM Services | App Ex | Abhishek T | Not Started | 2026-03-18
2.2 | Upload certificates to AWS certificate manager on target account (landing zone) | Cert Request | App Factory | Josh S | Blocked | 2026-03-19 | AD group (HON and Aero) required before requesting certificates
3 | Infrastructure Readiness |  |  |  | Not Started
3 | IAM Permission Mirroring/ Copy AMIs from source environement |  | App Factory | Srikanth K | In Progress
3.1 | Gather approval from VM team to use new AMI |  | App Factory | Josh S | Not Started
3.2 | Database migration planning |  | App Factory (DB Team) | Vasudevan KV | Not Started
3.3 | Deploy any VPC endpoints |  | App Factory | Josh S | Not Started
3.4 | Deploy serverless AWS services (RDS Database) |  | App Factory / App Ex | Josh S / Abhishek T | Not Started | 2026-03-16 | Require meeting with DB and App teams to confirm requirements. Tools available by AWS to perform. Working session required/complete
3.5 | Deploy compute instances |  | App Factory / App Ex | Josh S / Abhishek T | Not Started
3.6 | Deploy Security groups |  | App Factory | Josh S | Not Started
3.7 | Deploy Load Balancers |  | App Factory |  | N/A
3.8 | Create DNS entries for new load balancers |  | App Ex |  | N/A
3.9 | Confirm source, destination and port for traffic leaving the AWS Account |  | App Factory / App Ex | Josh S / Abhishek T | Not Started
3.1 | Submit Firewall Requests to make sure VPCs can communicate and downstream applications can receive outbound traffic |  | App Factory / App Ex | Josh S / Abhishek T | Not Started
3.11 | Test connecitvity post firewall request |  | App Factory | Josh S | Not Started
3.12 | Database migration |  | App Factory | Josh S | Not Started
3.13 | Verify connectivity to the newly migrated database |  | App Factory | Josh S | Not Started
3.14 | Service Readiness Verification |  | App Factory | Josh S | Not Started
3.15 | Handoff of completed resource tracker to Application Execution team |  | App Factory | Josh S | Not Started
4 | Application Readiness |  |  |  | Not Started
4 | Application Configuration |  | HON |  | Not Started
4.1 | Service Configuration |  | App Ex |  | Not Started
4.2 | Data Assessment |  | HON |  | Not Started
4.3 | Data Clean Up (if applicable) |  | HON |  | Not Started
4.4 | Data Validation (post clean up only) |  | HON |  | Not Started
4.5 | Configure CI/CD Pipelines (if applicable) |  | HON |  | Not Started
4.6 | Application Smoke Testing |  | HON |  | Not Started
4.7 | Complete Post-Migration Checklist |  | App Ex |  | Not Started
4.8 | Submit any final DNS requests |  | App Ex |  | Not Started
4.9 | Technical Support |  | App Factory |  | Not Started
5 | Rollback decision |  | App Ex |  | Not Started
5.1 | Rollback if required |  | App Ex |  | Not Started
5.2 | Complete Post-Migration Checklist (Post-Build) |  | App Ex |  | Not Started
5 | Application Testing |  |  |  | Not Started
5 | System Integration Testing (SIT) |  | App Ex |  | Not Started | 2026-03-25
5.1 | Review & Approval (TG2) |  | HONAERO |  | Not Started | 2026-03-26
5.2 | Regression Testing/ UAT |  | HONAERO |  | Not Started | 2026-03-27
5.3 | Technical Support |  | App Factory |  | Not Started

## Sheet3 (hidden)
Not Started
In Progress
Complete
Blocked
Delayed
N/A