## 1S4E_Prod
Migration Build Template - One Source For Engineering
| Application Name | ONESOURCE FOR ENGINEERING 8.0 PROD |  | App Profiling
| Function | R&D |  | Change Request #
| BAN | BAN0005525 |  | Disposition | AWS
| ASN | ASN0000261 |  | Database type(s)
| Environment | Prod |  | Current Install Type | AWS
| # Services | EC2, RDS |  | Application Type
| Source AWS Account | 464477000189 |  | Destination AWS Account
ID | Phase | Activities |  | Description | SOP Link | Team | Status
1 | Discovery & Design | jan | 1 jan | Identify the owners & source AWS account number – Business, Technical, and Site/ Run/ Service Owners and document the application summary tab of the application profile for a given Tranche​ that are working on | SOP 002 - Identify the owners – Business, Technical, and Site/ Run/ Service Owners​ | App Execution
1.1 | Discovery & Design | Verify App Execution team has the proper access to source AWS account and AERO AWS | 1.1 Verify App Execution team has the proper access to source AWS account and AERO AWS | Verify that all App Execution PwC team members who will be assisting with the application discovery and post-infrastructure configuration/setup have access to the source AWS account and the Aero AWS environement. | Cloud - AWS - Test Access to HON and AERO.docx | App Execution
1.2 | Discovery & Design | Verify App Factory team has the proper access to source AWS account and AERO AWS | 1.2 Verify App Factory team has the proper access to source AWS account and AERO AWS | Verify that all PwC team members who will be assisting with the application migration have access to the source AWS account and the Aero AWS environement. | Cloud - AWS - Test Access to HON and AERO.docx | App Factory
1.3 | Discovery & Design | Submit the Change Request | 1.3 Submit the Change Request | Provided this is a migration, a clone and migrate, ad flip, or any other "chanage" (i.e., not a new build), submit a change request through the honeywell change request process to get the build process started. | Change Request Creation SOP | App Execution
1.4 | Discovery & Design | Create an AERO/New Honeywell ASN | 1.4 Create an AERO/New Honeywell ASN | An Aero ASN needs to be generated before any Aero landing zone or resources can be created. |  | App Execution
1.5 | Discovery & Design | Update ASN Disposition | 1.5 Update ASN Disposition | Communicate with Application Service Owner the requirement to update the ASN disposition in CMDB prior to app migration, so CMDB data is maintained accrurately | SOP011.1 - IT Direct Process - BAN / ASN Create-Update | App Factory
1.6 | Discovery & Design | Gather Account Deployment Prerequisites | 1.6 Gather Account Deployment Prerequisites | SBU, SBE, App Name, ASN, BAC, USD Spend, AOP, 2 Contacts, Environment, Region, Networking | Create an AWS Landing Zone | App Execution
1.7 | Discovery & Design | AWS Account Setup (Landing Zone Creation) | 1.7 AWS Account Setup (Landing Zone Creation) | Deploy the AWS Landing Zone (AERO AWS account and VPC/Subnet provisioning) via ServiceNow | Create an AWS Landing Zone | App Execution
1.8 | Discovery & Design | Complete the AWS resource tracker & Open a teams chat (with app name) for this build | 1.8 Complete the AWS resource tracker & Open a teams chat (with app name) for this build | Create a copy of this form, save it to the worksteams sharepoint for each ASN and identify services and resources in the source AWS account that are needed in the target account. This will be used for both the build and tracking of cutover readiness. This form is critical to the cloud migration success since the CMDB data is incomplete for cloud. | Pattern 5 - Cloud Builds - Resource Tracker | App Execution (Primary) / App Factory (Secondary)
1.9 | Discovery & Design | Submit the Change Request | 1.9 Submit the Change Request | Provided this is a migration, a clone and migrate, ad flip, or any other "chanage" (i.e., not a new build), submit a change request through the honeywell change request process to get the build process started.
2.1 | Discovery & Design | Run CloudFormation IaC Generation for Discovery | 2.1 Run CloudFormation IaC Generation for Discovery | Run CloudFormation IaC generator on all resources for discovery and future template generation | Cloud - AWS - Essential - CloudFormation IaC Generator.docx | App Factory
2.2 | AWS Readiness Essentials | Create any AERO AD groups and required certificates | 2.2 Create any AERO AD groups and required certificates | Create any AERO AD groups needed to support the application (You will need this group for any SSL Certs). AD group members should be used for managing certificates with members being App Factory, App Execution, and App Owner. Typically just one group has been needed. Group needs to be created and certificate management team adds permissions on the backend. AD group creation in IT Direct. Certificate creation is managed through a distribution list. Certificates typically needed for ALBs. External - Honeywellaerospace.com signed by Digicert. | IAM Services Catalog.pptx | App Execution (Primary) / App Factory (Secondary)
2.3 | AWS Readiness Essentials | Upload certificates to AWS certificate manager on target account (landing zone) | 2.3 Upload certificates to AWS certificate manager on target account (landing zone) | Upload certificate(s) in AWS certificate manager |  | App Factory
3.1 | Infrastructure Readiness | IAM Permission Mirroring | 3.1 IAM Permission Mirroring | Mirror the permissions used by the application into the target AWS account. Discovery template should provide a list of users/roles/policies to be deployed in the target state. Use IaC generated cloudformation to upload to target. May need to change account number to target account in IaC before uploading. Use editor tools such as VScode in your VDI. For any credential creation for users you must contact Chris Clegg to provide these once users have been created. | IAM Permissions Creation SOP | App Factory
3.2 | Infrastructure Readiness | CI/CD Setup | 3.2 CI/CD Setup | Recreate any 3rd party CI/CD pipelines (CodePipeline, Jenkins, etc.) into the new AWS account. App execution team needs to get access to the deployment pipeline |  | App Execution
3.3 | Infrastructure Readiness | Database migration planning | 3.3 Database migration planning | Contact the PwC database team (Gautam/Andew T.) to start planning the database migration approach. |  | App Factory (DB Team)
3.4 | Infrastructure Readiness | Deploy any VPC endpoints | 3.4 Deploy any VPC endpoints | Deploy VPC endpoints that support the application or services. If using EC2s, you will need to set up the 3 specific SSM endpoints. Need to copy remaining endpoints from source account. | Cloud - AWS - VPC Endpoints & SSM Setup.docx | App Factory
3.5 | Infrastructure Readiness | Deploy serverless AWS services | 3.5 Deploy serverless AWS services | This can include Lambda functions, S3 buckets, SQS, SNS, and all other serverless AWS services using Cloudformation IaC and/or manual configuration. App factory to create function and bring over old code or deploy as hello world. App execution should be able to standup and configure their app components such as SQS, SNS, etc. |  | App Factory / App Execution - Joint
3.6 | Infrastructure Readiness | Deploy compute instances | 3.6 Deploy compute instances | EC2s (VMs) CAN ONLY BE DEPLOYED THROUGH SERVICENOW/VM TEAM. PwC is UNABLE TO DO THIS DIRECTLY. If AMI image(s) are present on source account, we need to find a way to share/move AMIs as private AMIs to target account. Honey well VM team contacts: Dylan Olson |  | App Factory / App Execution - Joint
3.7 | Infrastructure Readiness | Deploy Security groups | 3.7 Deploy Security groups | Configure security groups as deployed in source to the target. Deploy manually if its a small group and if large (10+ rules, etc.) deploy from IaC template. Look out for rules which have references to other security group IDs, etc. |  | App Factory
3.8 | Infrastructure Readiness | Deploy Load Balancers | 3.8 Deploy Load Balancers | Deploy ALB and NLB resources (reference uploaded certificates). Key watchout: public facing ALBs cannot directly see compute/web servers in the private web VPC. We need to set up a private NLB in the private web server VPC which can then be pointed to by the ALB. If it's a non-internet facing application, you can deploy the ALB directly in the private web VPC. |  | App Factory
3.9 | Infrastructure Readiness | Create DNS entries for new load balancers | 3.9 Create DNS entries for new load balancers | Create new Aero specific DNS entries for Load Balancers - App execution to now submit DNS request(s) and reference newly created load balancer information. |  | App Execution
3.1 | Infrastructure Readiness | Confirm source, destination and port for traffic leaving the AWS Account | 3.1 Confirm source, destination and port for traffic leaving the AWS Account | Collect all the relevant information about traffic leaving the AWS account for the target environment |  | App Factory / App Execution - Joint
3.11 | Infrastructure Readiness | CURRENT BLOCKER/ISSUE (NEED TO WORK WITH HONEYWELL TO RESOLVE/ESCALATE) Submit Firewall Requests to make sure VPCs can communicate and downstream applications can receive outbound traffic | 3.11 CURRENT BLOCKER/ISSUE (NEED TO WORK WITH HONEYWELL TO RESOLVE/ESCALATE) Submit Firewall Requests to make sure VPCs can communicate and downstream applications can receive outbound traffic | Submit 2 firewall requests: 1. Migration requirements between source and target AWS accounts. (Submitted by PwC) 2. Any traffic leaving a VPC that is required for the application to function. (Submitted by app owner) | Cloud - AWS - Essential - Networking & Firewall Requests.docx | App Factory / App Execution - Joint
3.12 | Infrastructure Readiness | Test connecitvity post firewall request | 3.12 Test connecitvity post firewall request | Verify all connecitivity is functional post |  | App Factory
3.13 | Infrastructure Readiness | Database migration | 3.13 Database migration | The database team can perform the database migration if ready |  | App Factory
3.14 | Infrastructure Readiness | Verify connectivity to the newly migrated database | 3.14 Verify connectivity to the newly migrated database | Open firewall request which allows database team to connect to the database in the target account through their VDI. Mirror the method used in the source account (IAM Auth, local db user, etc) and verify app teams and pwc team can connect |  | App Factory
3.15 | Infrastructure Readiness | Service Readiness Verification | 3.15 Service Readiness Verification | Review resources in the AWS Service Discovery Template and make sure everything is now deployed and configured |  | App Factory
3.16 | Infrastructure Readiness | Handoff of completed resource tracker to Application Execution team | 3.16 Handoff of completed resource tracker to Application Execution team | Complete a final check of target state readiness (all resources deployed, firewall request complete, etc.) and hand back completed resource tracker to app execution team. |  | App Factory
4.1 | Application Readiness | Application Configuration | 4.1 Application Configuration | Configure any IaaS level application changes for the target state | SOP069-Application Configuration | App Execution
4.2 | Application Readiness | Service Configuration | 4.2 Service Configuration | Configure any Service level changes for the target state | SOP070-Service Configuration | App Execution
4.3 | Application Readiness | Data Assessment | 4.3 Data Assessment |  | SOP 072 - Data Assessment and Validation-SOP | App Execution
4.4 | Application Readiness | Data Clean Up (if applicable) | 4.4 Data Clean Up (if applicable) |  |  | App Execution
4.5 | Application Readiness | Data Validation (post clean up only) | 4.5 Data Validation (post clean up only) |  | SOP 072 - Data Assessment and Validation-SOP | App Execution
4.6 | Application Readiness | Configure CI/CD Pipelines (if applicable) | 4.6 Configure CI/CD Pipelines (if applicable) |  | SOP074-Configure CICD Pipelines-SOP | App Execution
4.7 | Application Readiness | Application Smoke Testing | 4.7 Application Smoke Testing |  | SOP 77 Application Smoke Testing | App Execution
4.8 | Application Readiness | Complete Post-Migration Checklist (Post-Build) | 4.8 Complete Post-Migration Checklist (Post-Build) |  | SOP078 - Complete Post-Migration Checklist (Post-Build)-SOP.docx | App Execution
4.9 | Application Readiness | Submit any final DNS requests | 4.9 Submit any final DNS requests |  |  | App Execution
4.1 | Application Readiness | Technical Support | 4.1 Technical Support |  |  | App Factory
4.11 | Application Readiness | Rollback Decision Made | 4.11 Rollback Decision Made |  |  | App Execution
4.12 | Application Readiness | Rollback if required | 4.12 Rollback if required |  | SOP082_Rollback_If_Required_SOP.docx | App Execution
5.1 | Application Testing | System Integration Testing (SIT) | 5.1 System Integration Testing (SIT) |  | SOP094 System Integration Testing (SIT) - SOP | App Execution
5.2 | Application Testing | Review & Approval (TG2) | 5.2 Review & Approval (TG2) |  |  | App Execution
5.3 | Application Testing | Regression Testing/ UAT | 5.3 Regression Testing/ UAT |  | SOP095 Regression or UAT Testing | App Execution
5.4 | Application Testing | Technical Support | 5.4 Technical Support |  |  | App Execution
6.1 | Cutover and Hand-Off ​(Cutover for Production only) | Post cutover – Change Management and communication (TG3) (service owners)​ | 6.1 Post cutover – Change Management and communication (TG3) (service owners)​ |  | SOP097-Post cutover - Change Management and Communications - Service Owners (TG3)-SOP | App Execution
6.2 | Cutover and Hand-Off (Cutover for Production only) | KT Sessions ( 2 1-hour sessions)​ | 6.2 KT Sessions ( 2 1-hour sessions)​ |  |  | App Execution
6.3 | Cutover and Hand-Off (Cutover for Production only) | Final DNS Cleanup (Servers and VIPs) | 6.3 Final DNS Cleanup (Servers and VIPs) |  |  | App Execution
6.4 | Cutover and Hand-Off (Cutover for Production only) | Technical Support | 6.4 Technical Support |  |  | App Execution
7 | Hypercare | Technical Support | 7 Technical Support |  | Hypercare Technical Support | App Execution

## 1S4E_QA
AWS Migration Build Template - One Source For Engineering
| Application Name | ONESOURCE FOR ENGINEERING 8.0 QA |  | App Profiling
| Function | R&D |  | Change Request #
| BAN | BAN0005525 |  | Disposition | AWS
| ASN | ASN0000981 |  | Database type(s)
| Environment | QA |  | Current Install Type | AWS
| # Services | EC2, RDS |  | Application Type
| Source AWS Account | 361734395902 |  | Destination AWS Account
ID | Phase | Activities |  | Description | SOP Link | Team | Status
1 | Discovery & Design | Identify the owners – Business, Technical, and Site/ Run/ Service Owners​ / AWS account | 1 Identify the owners – Business, Technical, and Site/ Run/ Service Owners​ / AWS account | Identify the owners & source AWS account number – Business, Technical, and Site/ Run/ Service Owners and document the application summary tab of the application profile for a given Tranche​ that are working on | SOP 002 - Identify the owners – Business, Technical, and Site/ Run/ Service Owners​ | App Execution | Done
1.1 | Discovery & Design | Verify App Execution team has the proper access to source AWS account and AERO AWS | 1.1 Verify App Execution team has the proper access to source AWS account and AERO AWS | Verify that all App Execution PwC team members who will be assisting with the application discovery and post-infrastructure configuration/setup have access to the source AWS account and the Aero AWS environement. | Cloud - AWS - Test Access to HON and AERO.docx | App Execution | Vikesh
1.2 | Discovery & Design | Verify App Factory team has the proper access to source AWS account and AERO AWS | 1.2 Verify App Factory team has the proper access to source AWS account and AERO AWS | Verify that all PwC team members who will be assisting with the application migration have access to the source AWS account and the Aero AWS environement. | Cloud - AWS - Test Access to HON and AERO.docx | App Factory | Done
1.3 | Discovery & Design | Submit the Change Request | 1.3 Submit the Change Request | Provided this is a migration, a clone and migrate, ad flip, or any other "chanage" (i.e., not a new build), submit a change request through the honeywell change request process to get the build process started. | Change Request Creation SOP | App Execution | Vikesh
1.4 | Discovery & Design | Create an AERO/New Honeywell ASN | 1.4 Create an AERO/New Honeywell ASN | An Aero ASN needs to be generated before any Aero landing zone or resources can be created. |  | App Execution | Vikesh
1.5 | Discovery & Design | Update ASN Disposition | 1.5 Update ASN Disposition | Communicate with Application Service Owner the requirement to update the ASN disposition in CMDB prior to app migration, so CMDB data is maintained accrurately | SOP011.1 - IT Direct Process - BAN / ASN Create-Update | App Factory | Mutthu
1.6 | Discovery & Design | Gather Account Deployment Prerequisites | 1.6 Gather Account Deployment Prerequisites | SBU, SBE, App Name, ASN, BAC, USD Spend, AOP, 2 Contacts, Environment, Region, Networking | Create an AWS Landing Zone | App Execution | Done for Non Prod AERO Pending for Non Prod New Honeywell | Aero Non Prod EC2 has been configured HW , once LZ is done then RFC will be rasied for EC2 | Check with Ravif for Prod Code Freeze Dates
1.7 | Discovery & Design | AWS Account Setup (Landing Zone Creation) | 1.7 AWS Account Setup (Landing Zone Creation) | Deploy the AWS Landing Zone (AERO AWS account and VPC/Subnet provisioning) via ServiceNow | Create an AWS Landing Zone | App Execution | Done for Non Prod AERO Pending for Non Prod New Honeywell | WIP
1.8 | Discovery & Design | Complete the AWS resource tracker & Open a teams chat (with app name) for this build | 1.8 Complete the AWS resource tracker & Open a teams chat (with app name) for this build | Create a copy of this form, save it to the worksteams sharepoint for each ASN and identify services and resources in the source AWS account that are needed in the target account. This will be used for both the build and tracking of cutover readiness. This form is critical to the cloud migration success since the CMDB data is incomplete for cloud. | Pattern 5 - Cloud Builds - Resource Tracker | App Execution (Primary) / App Factory (Secondary) | Vikesh, and Srikanth check
1.9 | Discovery & Design | Submit the Change Request | 1.9 Submit the Change Request | Provided this is a migration, a clone and migrate, ad flip, or any other "chanage" (i.e., not a new build), submit a change request through the honeywell change request process to get the build process started. |  | App Execution | Jason/ Abhi/ Vikesh
2.1 | Discovery & Design | Run CloudFormation IaC Generation for Discovery | 2.1 Run CloudFormation IaC Generation for Discovery | Run CloudFormation IaC generator on all resources for discovery and future template generation | Cloud - AWS - Essential - CloudFormation IaC Generator.docx | App Factory | Done
2.2 | AWS Readiness Essentials | Create any AERO AD groups and required certificates | 2.2 Create any AERO AD groups and required certificates | Create any AERO AD groups needed to support the application (You will need this group for any SSL Certs). AD group members should be used for managing certificates with members being App Factory, App Execution, and App Owner. Typically just one group has been needed. Group needs to be created and certificate management team adds permissions on the backend. AD group creation in IT Direct. Certificate creation is managed through a distribution list. Certificates typically needed for ALBs. External - Honeywellaerospace.com signed by Digicert. | IAM Services Catalog.pptx | App Execution (Primary) / App Factory (Secondary) | Who will give the name of AD groups which need to be created, and check with Jan Horky and Vikesh
2.3 | AWS Readiness Essentials | Upload certificates to AWS certificate manager on target account (landing zone) | 2.3 Upload certificates to AWS certificate manager on target account (landing zone) | Upload certificate(s) in AWS certificate manager |  | App Factory | to be started
3.1 | Infrastructure Readiness | IAM Permission Mirroring | 3.1 IAM Permission Mirroring | Mirror the permissions used by the application into the target AWS account. Discovery template should provide a list of users/roles/policies to be deployed in the target state. Use IaC generated cloudformation to upload to target. May need to change account number to target account in IaC before uploading. Use editor tools such as VScode in your VDI. For any credential creation for users you must contact Chris Clegg to provide these once users have been created. | IAM Permissions Creation SOP | App Factory | Done
3.2 | Infrastructure Readiness | CI/CD Setup | 3.2 CI/CD Setup | Recreate any 3rd party CI/CD pipelines (CodePipeline, Jenkins, etc.) into the new AWS account. App execution team needs to get access to the deployment pipeline |  | App Execution | Not Applicable
3.3 | Infrastructure Readiness | Database migration planning | 3.3 Database migration planning | Contact the PwC database team (Gautam/Andew T.) to start planning the database migration approach. |  | App Factory (DB Team) | Jason to share update received from DB team Tanaji/ Rutuja Not started , in discussion phase | Check QA to QA or Prod to QA check with Jan Horky DB Team can start with Non Prod Aero right away
3.4 | Infrastructure Readiness | Deploy any VPC endpoints | 3.4 Deploy any VPC endpoints | Deploy VPC endpoints that support the application or services. If using EC2s, you will need to set up the 3 specific SSM endpoints. Need to copy remaining endpoints from source account. | Cloud - AWS - VPC Endpoints & SSM Setup.docx | App Factory | SSM is done VPC endpoints Not Applicable
3.5 | Infrastructure Readiness | Deploy serverless AWS services | 3.5 Deploy serverless AWS services | This can include Lambda functions, S3 buckets, SQS, SNS, and all other serverless AWS services using Cloudformation IaC and/or manual configuration. App factory to create function and bring over old code or deploy as hello world. App execution should be able to standup and configure their app components such as SQS, SNS, etc. |  | App Factory / App Execution - Joint | Not Applicable
3.6 | Infrastructure Readiness | Deploy compute instances | 3.6 Deploy compute instances | EC2s (VMs) CAN ONLY BE DEPLOYED THROUGH SERVICENOW/VM TEAM. PwC is UNABLE TO DO THIS DIRECTLY. If AMI image(s) are present on source account, we need to find a way to share/move AMIs as private AMIs to target account. Honey well VM team contacts: Dylan Olson |  | App Factory / App Execution - Joint | Done
3.7 | Infrastructure Readiness | Deploy Security groups | 3.7 Deploy Security groups | Configure security groups as deployed in source to the target. Deploy manually if its a small group and if large (10+ rules, etc.) deploy from IaC template. Look out for rules which have references to other security group IDs, etc. |  | App Factory | Done
3.8 | Infrastructure Readiness | Deploy Load Balancers | 3.8 Deploy Load Balancers | Deploy ALB and NLB resources (reference uploaded certificates). Key watchout: public facing ALBs cannot directly see compute/web servers in the private web VPC. We need to set up a private NLB in the private web server VPC which can then be pointed to by the ALB. If it's a non-internet facing application, you can deploy the ALB directly in the private web VPC. |  | App Factory | Not Applicable
3.9 | Infrastructure Readiness | Create DNS entries for new load balancers | 3.9 Create DNS entries for new load balancers | Create new Aero specific DNS entries for Load Balancers - App execution to now submit DNS request(s) and reference newly created load balancer information. |  | App Execution | Not Applicable
3.1 | Infrastructure Readiness | Confirm source, destination and port for traffic leaving the AWS Account | 3.1 Confirm source, destination and port for traffic leaving the AWS Account | Collect all the relevant information about traffic leaving the AWS account for the target environment |  | App Factory / App Execution - Joint | to be started, can be done in parallel Infra - App Factory Cloud Team App related- App Execution needs to get in touch with App owner
3.11 | Infrastructure Readiness | CURRENT BLOCKER/ISSUE (NEED TO WORK WITH HONEYWELL TO RESOLVE/ESCALATE) Submit Firewall Requests to make sure VPCs can communicate and downstream applications can receive outbound traffic | 3.11 CURRENT BLOCKER/ISSUE (NEED TO WORK WITH HONEYWELL TO RESOLVE/ESCALATE) Submit Firewall Requests to make sure VPCs can communicate and downstream applications can receive outbound traffic | Submit 2 firewall requests: 1. Migration requirements between source and target AWS accounts. (Submitted by PwC) 2. Any traffic leaving a VPC that is required for the application to function. (Submitted by app owner) | Cloud - AWS - Essential - Networking & Firewall Requests.docx | App Factory / App Execution - Joint | WIP by App Factory Cloud Team
3.12 | Infrastructure Readiness | Test connecitvity post firewall request | 3.12 Test connecitvity post firewall request | Verify all connecitivity is functional post |  | App Factory
3.13 | Infrastructure Readiness | Database migration | 3.13 Database migration | The database team can perform the database migration if ready |  | App Factory
3.14 | Infrastructure Readiness | Verify connectivity to the newly migrated database | 3.14 Verify connectivity to the newly migrated database | Open firewall request which allows database team to connect to the database in the target account through their VDI. Mirror the method used in the source account (IAM Auth, local db user, etc) and verify app teams and pwc team can connect |  | App Factory
3.15 | Infrastructure Readiness | Service Readiness Verification | 3.15 Service Readiness Verification | Review resources in the AWS Service Discovery Template and make sure everything is now deployed and configured |  | App Factory
3.16 | Infrastructure Readiness | Handoff of completed resource tracker to Application Execution team | 3.16 Handoff of completed resource tracker to Application Execution team | Complete a final check of target state readiness (all resources deployed, firewall request complete, etc.) and hand back completed resource tracker to app execution team. |  | App Factory
4.1 | Application Readiness | Application Configuration | 4.1 Application Configuration | Configure any IaaS level application changes for the target state | SOP069-Application Configuration | App Execution | one any IaaS Not Applicable
4.2 | Application Readiness | Service Configuration | 4.2 Service Configuration | Configure any Service level changes for the target state | SOP070-Service Configuration | App Execution | one any Service Not Spplicable
4.3 | Application Readiness | Data Assessment | 4.3 Data Assessment |  | SOP 072 - Data Assessment and Validation-SOP | App Execution | Not Applicable
4.4 | Application Readiness | Data Clean Up (if applicable) | 4.4 Data Clean Up (if applicable) |  |  | App Execution | Not Applicable
4.5 | Application Readiness | Data Validation (post clean up only) | 4.5 Data Validation (post clean up only) |  | SOP 072 - Data Assessment and Validation-SOP | App Execution | Not Applicable
4.6 | Application Readiness | Configure CI/CD Pipelines (if applicable) | 4.6 Configure CI/CD Pipelines (if applicable) |  | SOP074-Configure CICD Pipelines-SOP | App Execution | Not Applicable
4.7 | Application Readiness | Application Smoke Testing | 4.7 Application Smoke Testing |  | SOP 77 Application Smoke Testing | App Execution | Not Applicable
4.8 | Application Readiness | Complete Post-Migration Checklist (Post-Build) | 4.8 Complete Post-Migration Checklist (Post-Build) |  | SOP078 - Complete Post-Migration Checklist (Post-Build)-SOP.docx | App Execution | Not Applicable
4.9 | Application Readiness | Submit any final DNS requests | 4.9 Submit any final DNS requests |  |  | App Execution | Not Applicable
4.1 | Application Readiness | Technical Support | 4.1 Technical Support |  |  | App Factory | Not Applicable
4.11 | Application Readiness | Rollback Decision Made | 4.11 Rollback Decision Made |  |  | App Execution | Not Applicable
4.12 | Application Readiness | Rollback if required | 4.12 Rollback if required |  | SOP082_Rollback_If_Required_SOP.docx | App Execution | Rbne
5.1 | Application Testing | System Integration Testing (SIT) | 5.1 System Integration Testing (SIT) |  | SOP094 System Integration Testing (SIT) - SOP | App Execution | Not Applicable
5.2 | Application Testing | Review & Approval (TG2) | 5.2 Review & Approval (TG2) |  |  | App Execution | Not Applicable
5.3 | Application Testing | Regression Testing/ UAT | 5.3 Regression Testing/ UAT |  | SOP095 Regression or UAT Testing | App Execution | Not Applicable
5.4 | Application Testing | Technical Support | 5.4 Technical Support |  |  | App Execution | Not Applicable
6.1 | Cutover and Hand-Off ​(Cutover for Production only) | Post cutover – Change Management and communication (TG3) (service owners)​ | 6.1 Post cutover – Change Management and communication (TG3) (service owners)​ |  | SOP097-Post cutover - Change Management and Communications - Service Owners (TG3)-SOP | App Execution | Not Applicable
6.2 | Cutover and Hand-Off (Cutover for Production only) | KT Sessions ( 2 1-hour sessions)​ | 6.2 KT Sessions ( 2 1-hour sessions)​ |  |  | App Execution | Not Applicable
6.3 | Cutover and Hand-Off (Cutover for Production only) | Final DNS Cleanup (Servers and VIPs) | 6.3 Final DNS Cleanup (Servers and VIPs) |  |  | App Execution | Not Applicable
6.4 | Cutover and Hand-Off (Cutover for Production only) | Technical Support | 6.4 Technical Support |  |  | App Execution | Not Applicable
7 | Hypercare | Technical Support | 7 Technical Support |  | Hypercare Technical Support | App Execution | Not Applicable